## Slide 1: Tagger Microscope and Diamond Fabrication
Alex Barnes, Ann Marie Carroll, James McIntyre, Brendan Pratt
Feb. 20-22, 2014
GlueX Collaboration Meeting

## Slide 2: Outline
Update on fiber construction
  Process overview
  Current status and schedule
Update on final enclosure
Update on electronics and fiber QA
  Current status on electronics
  Current progress on fiber QA
Diamond fabrication
  Ablating status, schedule, explain purchasing process

## Slide 3: Fiber Bundle Overview
light guide fibers
2 cm of scintillating fiber fused to 167 cm of lightguide fiber
30 fused fibers bundled (5x6) together
17 bundles of 30 fibers each
Painted and glued before large bend
Spread out after large bend
Each fiber terminates 0.5 mm above a SiPM
SiPMs

## Slide 4: Rough Cut and Measure
800 m of total lightguide fiber used. 166.6 cm long segments.
Each lightguide measured for conformity in 5 places.
Step complete

## Slide 5: Straightening
Step complete

## Slide 6: End Milling
Step complete
Both scintillating and
lightguide fibers are cut
to final size in the physics
machine shop.

## Slide 7: Polishing
Step complete
Before
After

## Slide 8: Fusing
Step complete
AV photo lamp
Fibers enclosed in quartz ferrules
Tangential and linear pressure controls
Fuses hold 800 – 1000 g of transverse weight before breaking
  Stronger than optical epoxy
  More than enough strength to withstand bending

## Slide 9
Bending
Fused fibers are bundled together
S-bend in bundled fibers on one end
Fibers spread out into chimneys at the other end
Heated up to 1600 F over a 12 hour period, then bent

## Slide 10
After Bending
7 of 17 bundles bent

## Slide 11: Painting
Water based titanium dioxide paint
10-20 microns thick
Painted only where fibers will contact one another
5 of 17 bundles painted

## Slide 12
Gluing
1 of 17 bundles glued… more to be glued soon!
Glued through straight portion
Fibers permanently
attached to metal mount

## Slide 13: Shipping Preparations
Fibers strapped to Styrofoam
Traveler documentation included in with each bundle
Fibers will travel with members of the UConn team to JLab
Traveler Documentation (stored here)

## Slide 14: Schedule for Completion of Fiber Bundles
Bend 2 bundles per week
5 weeks until all fibers are bent
When not bending, paint and glue
New completion date of April 8, 2014

## Slide 15: Upper & Lower Enclosures
Currently have 238 of 364 required components
Work at 2 of 4 machine shops complete
Last 126 components scheduled to arrive < 2 weeks

## Slide 16: Electronics
Undergraduate researcher is calibrating the DAC offsets on the control boards
Fernando, Nick and Chris have finished attaching and testing the SiPMs on the preamps
Boards have arrived at UConn
Already have 2 which are being used for fiber QA

## Slide 17: Fiber QA
Feb. 20-22, 2014

## Slide 18: Relative comparison between fibers
Fully painted fiber
Averaged over all events
Pulse integral of 275 pixels
Unpainted fiber
Averaged over all events
Pulse integral of 636 pixels
Partially painted fiber
Averaged over all events
Pulse integral of 248 pixels
Channels triggered by separate pulser circuit
All channels measured at the same time
Single pixel = ~1 ADC count

## Slide 19: Diamonds:2014
Brendan Pratt
Richard Jones
University of Connecticut

## Slide 20
best yet,
but took >40 hours
From 18 months ago…

## Slide 21
Much faster,
but sometimes too quick!

## Slide 22
Translation stage moves in X while laser continues to pulse
focused laser pulse
is there a better idea?

## Slide 23
3x3x0.3mm crystal
2.6mmx2.6mm window
Apparent gradient from tilt on microscope table

## Slide 25
about 50μm depth
cut through X
cut through Y
After 18 passes

## Slide 26
Ablated diamond,
nearly as smooth as butter
Butter
(not real butter data)
RMS about 400nm
Much better than +/-5micron spec

## Slide 27: Conclusions from new raster
Excellent surface uniformity
Retains picture frame and steep edges
Cuts uniformly over long periods of time
Each pass is completed on the order of 15min (for 2.6x2.6mm2) active area, with a cut rate of 3microns per pass.
Cut rate scales with area

## Slide 28: Upcoming Diamond Milestones UConn